### 9. Communication Management Plan

Each group of stakeholders will be provided with specific information at set intervals. All communication will be done via one owned channel. Project artefacts will be stored using GitHub as the single source of truth. There will be discussions and meetings via Microsoft Teams, but emails will only be sent for official approvals and organisation wide communications.

### 9.1 Communication matrix

| Item | Audience | Purpose | Frequency | Channel | Owner |
| --- | --- | --- | --- | --- | --- |
| Daily stand-up | Core team, integration partner | Progress, plans, blockers | Daily, 15 min (build and test phases) | Teams call; GitHub board | PM |
| Weekly status report | Sponsor, CISO, steering committee | Schedule and cost variance, top risks, P1/P2 issues, decisions needed | Weekly, Friday | Email (PDF from GitHub wiki) | PM |
| Steering committee | CIO, CISO, CFO, HR manager, PM | Gate decisions, escalations, budget | Monthly and at each gate | Meeting with minutes | PM |
| Change Control Board | CCB members | Decide change requests | Weekly, Wednesday | Teams meeting; CR issues | PM |
| Sprint review and demo | Core team, business representatives | Show completed build items, gather feedback | Every 2 weeks (Phase 3) | Teams demo | IAM Architect |
| Board risk update | Board Risk Committee | CPS 234 progress and residual risk | Monthly | Paper via CIO | CIO with PM input |
| Staff updates | All 620 staff | What is changing, when and what to do | Fortnightly from May; weekly during rollout | Intranet, email, branch huddles | Change, Comms and Config Lead |
| Branch rollout pack | Branch managers | Wave dates, checklist, support contacts | 2 weeks before each wave | Email and briefing call | Change, Comms and Config Lead |
| Service desk briefing | Service desk | Known issues, runbooks, escalation | Before pilot and each wave; daily in hypercare | Teams; knowledge base | Integration and Test Lead |
| Vendor stand-up | Vendor, integration partner, IAM Architect | Technical progress and defects | Weekly | Teams | IAM Architect |
| Lessons learned | All stakeholders | Improve future projects | At each gate and at closure | Workshop; GitHub wiki | PM |

### 9.2 Escalation path

The information flows from team member to work package owner then to Project Manager, Sponsor (CIO) and steering committee. However any security issues must be reported directly to the CISO following the incident management plan within CCU. This includes reporting to APRA within 72 hours of a material information security incident within the CPS 234 requirement (APRA, 2019).

### 9.3 Communication principles

- Single message source – All communication to staff is approved by the Change, Comms and Config Lead and HR manager.

- No jargon – Messages will be written in clear language. For example, ‘security key’ rather than ‘FIDO2 authoriser’.

- All meeting notes and decisions are recorded in the GitHub wiki within 24 hrs (see template in appendix C).

- All status reports will follow the same definition of RAG status (Red, Amber, Green) to ensure consistent trends.

## 10. Quality management approach

Quality is defined as meeting the acceptance criteria in Section 2.4 and the security standards CCU is held to. The approach follows the plan–do–check–act cycle: quality planning sets standards and metrics, quality assurance checks that the process is followed, and quality control tests the deliverables.

### 10.1 Quality standards applied

- APRA CPS 234- information security roles, controls, testing and incident notification.

- ACSC Essential Eight includes multi factor authentication and limiting admin rights to maturity level 2.

- Authentication assurance according to NIST SP 800-63B-4. Admins and core banking users will be at AAL3 (Phishing resistant hardware bound keys). All other staff will be at AAL2. (Temoshok et al., 2025)

- Access controls per ISO/IEC 27001:2022 (Annex A 5.15-5.18 and 8.2-8.5). (ISO & IEC, 2022)

- Project management practices from the PMBOK Guide to manage the scope, timeline, risks and quality of the project. (PMI, 2025)

### 10.2 Quality metrics

| Metric | Target | Measured by | When |
| --- | --- | --- | --- |
| Requirements traced to test cases | 100% | Traceability matrix in GitHub | Before SIT |
| SIT test pass rate | 95% first run; 100% before UAT exit | Test management log | 4.1 |
| Open defects at go-live | 0 critical, 0 high, ≤ 10 medium with workarounds | GitHub issues label:defect | M2 |
| Penetration test findings | 0 critical or high unresolved | Pen test report | 4.2 |
| SSO login success rate in pilot | ≥ 99% | IdP sign-in logs | 5.1 |
| Leaver de-provisioning time | ≤ 4 hours for 100% of leavers | IGA audit report | Weekly from 5.3 |
| MFA enrolment | 100% of staff | IdP dashboard | 18 Aug 2027 |
| User satisfaction after rollout | ≥ 4 out of 5 | Pulse survey | 6.1 |
| Documents peer-reviewed before approval | 100% | Pull request approvals | Ongoing |

### 10.3 Quality assurance activities

- All Plans and Design documents peer reviewed via GitHub pull request process. Minimum 1 reviewer required (non-author).

- Design gate at M1 includes Architecture Review Board.

- Security review will be performed by CCU internal audit team. All CPS 234 controls will be reviewed to ensure evidence is provided. This will be completed prior to going live.

- PM will perform a process audit. Are risks, issues and CRs being recorded and up to date?

- Lessons learned captured at all gates.

### 10.4 Quality control activities

| Test level | What is tested | Who | Exit criteria |
| --- | --- | --- | --- |
| Unit and configuration checks | Each policy, connector and workflow as built | Integration engineers | Configuration checklist complete; automated policy checks pass |
| System integration testing (SIT) | End-to-end flows: HR joiner to app access, mover, leaver, SSO, MFA, PAM checkout | Integration and Test Lead | 100% of SIT cases passed or deferred by CCB |
| Penetration test | IdP, PAM, admin interfaces, MFA bypass attempts | CREST-accredited third party | No critical or high findings open |
| User acceptance testing (UAT) | 45 business scenarios across 6 departments | Business testers, Test Lead | Signed UAT certificate from each department head |
| Operational acceptance | Backup, monitoring, break-glass, runbooks | Service desk and operations | Operations manager sign-off |

Defects are logged as GitHub issues with a severity label and linked to the failed test case. A defect review is held daily during SIT and UAT.

## 11. Configuration management using GitHub

All of our project documentation, including our IAM infrastructure as code and tracking tools are stored in one private GitHub repo. We make use of Git to keep track of all versioning. We also ensure we have branch protection to only allow changes that have been reviewed into our approved baseline. Tags are applied to denote an approved baseline so we can always provide what has been approved and when to auditors.

### 11.1 Why GitHub

GitHub has been selected as the source control tool as it offers several features including: Issues (risk/issue/defect/change log), Projects (Kanban board/roadmap view of the schedule), Pull requests (peer review and proof of approval), Wiki (minutes/status reports) and Actions (automated testing) all in one place. The free plan allows for private repositories with other collaborators meaning it fits the requirements of our group. This has been compared to other tools such as GitLab and Bitbucket.

### 11.2 Configuration items (CIs)

| Configuration item | Location in repository | Baseline at | Change approval |
| --- | --- | --- | --- |
| Project charter and this plan | /docs/plan/ | Charter approval (v1.0) | CCB |
| Requirements and traceability matrix | /docs/requirements/ | M1 | CCB |
| Solution architecture and RBAC role model | /docs/design/ | M1 | CCB with Architecture Review Board |
| Schedule and budget | /docs/plan/schedule/ and GitHub Projects | M1 | CCB |
| Risk, issue and change registers | GitHub Issues with labels risk, issue, change-request | Live | PM |
| IAM policies and connector configuration (as code) | /config/ (Terraform and JSON exports) | M2 | CCB and CAB |
| Test plans, scripts and results | /tests/ | M2 | Test Lead |
| Training materials and runbooks | /docs/training/, /docs/runbooks/ | M2 | Change Lead and Ops manager |

Secrets (API keys, passwords, certificates) are never committed. They are stored in the PAM vault; a .gitignore and GitHub secret scanning with push protection block accidental commits.

### 11.3 Repository structure

The repository is organised into the following folders:

| Folder or file | What it contains |
| --- | --- |
| README.md | Purpose of the repository, how to contribute, contacts |
| CONTRIBUTING.md | Branching, commit and review rules |
| CHANGELOG.md | Summary of each tagged baseline |
| .github/CODEOWNERS | Who must review which folders |
| .github/ISSUE_TEMPLATE/ | Forms for risks, issues, change requests and defects |
| .github/pull_request_template.md | Checklist shown on every pull request |
| .github/workflows/docs-check.yml | Automatic markdown and link checks |
| docs/ | Sub-folders: plan, requirements, design, training, runbooks, meetings |
| config/ | IAM policy and connector configuration exports |
| tests/ | SIT and UAT test scripts and results |

### 11.4 Branching and review workflow

The team uses GitHub Flow, a simple trunk-based model suited to a small team:

1. Main contains the version of each item approved and is protected. No direct pushes, 1+ approvals, required status checks and linear history (GitHub, n.d.)

2. Each piece of work has a feature branch with a descriptive name indicating what the branch is for. Branch names will follow this format: docs/42-risk-register-update, config/57-mfa-policy, cr/63-add-payroll-app

3. Commit messages are descriptive and include reference to the issue. Example: Update R2 mitigation after data audit (#42)

4. A pull request is raised early. This will be created as a draft. The correct reviewer is requested using the CODEOWNERS file. For example, the PM will be requested for /docs/plan/, the IAM Architect for /docs/design/ and /config/.

5. A GitHub Actions check is run on all pull requests. The PR can only be merged once all checks have passed and the reviewer has approved. This will close the linked issue.

6. At each gate, the PM will create an annotated tag. A GitHub Release is created with the following tags: v1.0-charter, v2.0-design-baseline, v3.0-go-live, v4.0-closure. Notes will be added to the CHANGELOG.md.The basic Git commands used by the team are shown below:

git checkout main && git pull
git checkout -b docs/42-risk-register-update
# edit files
git add docs/plan/risk-register.md
git commit -m “Update R2 mitigation after data audit (#42)”
git push -u origin docs/42-risk-register-update
# open pull request on GitHub, request review, merge after approval
git tag -a v2.0-design-baseline -m “Design baseline approved at M1, 12 Apr 2027”
git push origin v2.0-design-baseline

### 11.5 Configuration status accounting and audit

- Status accounting – the GitHub Projects board shows every work item as Backlog, In progress, In review or Done, and the Insights tab shows commit and PR activity by member, which also serves as evidence of each member’s contribution to this assessment.

- Configuration audit – before each gate the Change, Comms and Config Lead checks that every CI in Section 11.2 is at its expected version, that no unmerged branches touch baselined items and that the release notes match the CCB decisions.

- Traceability – each change request issue links to its pull request, commits and tag, so any change can be traced from request to approved baseline.

- Access control – repository access uses CCU’s SSO and MFA once live; members have Write access, the PM and Config Lead have Maintain, and branch protection rules apply to administrators too.

## 12. Conclusion

This solution provides a controlled implementation of an IAM solution at Coastal Credit Union, reducing their fragmented manual solution to a single solution and addressing the issues raised in their audit report causing them to be non-compliant with CPS 234. The 32 week timeline has been planned using clear dependencies and a calculated critical path to ensure that they have 18 activities that are fixed and cannot be delayed and some float activities to allow for any issues.

By addressing the biggest risks of poor HR data quality and core banking integration early in the audit and vendor proof of concept stages there is an increased assurance that the solution will be delivered. By implementing change control, escalation processes, clear quality gates and configuration management using GitHub everything will be documented to show the decisions made throughout the project. Delivering as planned will increase CCU to Essential Eight Maturity Level 2 for Identity Controls and improve their leaver access to hours rather than days.